## Reference
When planning the project, ensure each of the following items are taken into consideration and included in the budget if applicable:
What | Approximate Cost | Notes
PCI Compliance | $3,000 - $5,000 | Only if the service handles money / takes payments
STRA | $2,000 - $5,000 | Outsource if needed
PIA Completion | $2,000 - $3,000 | Can be completed by the YG Corporate Information Security Officer (CISO) or outsourced to vendor
FR Translation |  | May be completed by the internal YG team, may be outsourced
Domain registration | $50 - $150 | Could be upwards of several thousand if a domain squatter holds the domain
Code Change Management | $10,000 - $12,000
Security certificate
Vendor costs | varies | Estimated with each vendor (development/design/prototype development, beta, etc.)

## Plan
Project information
Project name:
Service owner:
Service Delivery Manager:
Project manager:
Total Estimated Project Budget | <What is the total budget allocated to this project? Is it from different sources or across fiscal years?>
Planned Budget Tracker
Reference | Description | Amount
Contract ID | Description (JV or capital), authorizing branch, etc
| Total: | 0

## ByMonthTracking
|  | BUDGET | [5 empty] | SCHEDULE
Contract # | Project name | Budget status | Invoice # | Total Contract Budget | Expended (this month) | Total expended to date | Remaining Contract Amount | Target project complete date | Schedule status | Scope status | Effort Estimate to Complete | Comments
C00sample | Sample example project | On track |  | 65000 | 12000 | 48000 | 17000 | 2020-03-21 | On track | At risk
<paste these in as received from the project vendors>